Standard Operating Procedure

Quality Improvement Projects

«Hospital Name» — Supports PSQ.4

Why does this SOP exist? (read this first if you're new) The purpose of this policy is to establish a structured approach for planning, conducting, documenting and reviewing quality improvement projects. This policy does not cover matters outside quality improvement projects. If you're new to patient safety and quality work, the short version is: this SOP tells you exactly what to do, in what order, and which record proves you did it.

| SOP No. | [Hospital to define] | Version | 1.0 |
| --- | --- | --- | --- |
| Effective Date | ________ | Review Frequency | Annual, or on change |
| Prepared By | Quality Coordinator Name: ________ Signature: ________ |  |  |
| Approved By | Medical Superintendent Name: ________ Signature: ________ |  |  |

# 1. Purpose

The purpose of this policy is to establish a structured approach for planning, conducting, documenting and reviewing quality improvement projects. This policy does not cover matters outside quality improvement projects.

# 2. Scope

This policy applies to quality improvement projects undertaken by «Hospital Name».

# 3. Responsibility

Quality Coordinator: leads day-to-day work on this policy and owns the required records.

Safety/Quality Committee: reviews progress on this policy at least monthly and signs off the annual review.

Department Heads: carry out the parts of this policy that apply within their own department.

Medical Superintendent / Governing Body: provides resources and reviews outcomes reported to them.

All staff in scope: follow the steps below and raise any Stop-Work concern immediately, without waiting for permission.

# 4. Plain-Language Glossary

If a word below is unfamiliar, this is what it means in this SOP:

PROMs: Patient-Reported Outcome Measures — questionnaires patients fill in themselves about how they're doing.

PDSA: Plan-Do-Study-Act — a simple cycle for testing a change before rolling it out everywhere.

DMAIC: Define–Measure–Analyze–Improve–Control — a structured Six Sigma method for fixing a bigger, data-heavy process problem, more rigorous than a single PDSA cycle.

EQ-5D: A short, standard questionnaire patients fill in themselves, scoring 5 areas of health (mobility, self-care, usual activities, pain/discomfort, anxiety/depression) plus an overall visual scale — used to measure a treatment's real-world impact from the patient's point of view.

MCID (Minimal Clinically Important Difference): The smallest change in a score (like a PROM) that a patient would actually notice and consider worthwhile — used to judge whether an improvement is real, not just statistical noise.

# 5. Procedure

## 5.1 Plan and select projects

Why this step matters: A project chosen because it 'seemed useful' instead of a real data-driven reason wastes a year that could have gone toward an actual risk.

1. Select at least 2 quality improvement projects per year, each justified by a real reason — a high-risk, high-volume or problem-prone process, or a finding from an indicator, incident analysis, or patient-reported data — not “seemed useful.”

2. Document the selection rationale in the project plan before work starts.

Technical source(s) for these steps:

National Accreditation Board for Hospitals and Healthcare Providers. (2025). NABH accreditation standards for hospitals (6th ed.), PSQ.4. ISBN 978-81-965264-9-8. https://portal.nabh.co/images/Standards/NABH%20Hospital%20Accreditation%20Standard%206th%20Edition%20January%202025.pdf

## 5.2 Follow a structured approach

Why this step matters: An improvement attempted without a named, repeatable method can't be judged as having worked or not — there's nothing to compare the result against.

1. Run the project as a PDSA cycle (Plan–Do–Study–Act, small-scale iterative testing) for a fast, incremental change, or as Six Sigma DMAIC (Define–Measure–Analyze–Improve–Control) for a larger, statistically complex process problem — name whichever method was actually used in the project record.

Technical source(s) for these steps:

Institute for Healthcare Improvement, as summarized by Minnesota Department of Health. (n.d.). Plan-Do-Study-Act (PDSA).

National Center for Biotechnology Information. (2023). Define, Measure, Analyze, Improve, Control (DMAIC) methodology as a roadmap in quality improvement.

## 5.3 Document project outcomes

Why this step matters: 'It got better' without the actual before-and-after number isn't evidence — it's an impression that evaporates the moment someone asks for proof.

1. On completion, document whether the stated goal was actually achieved — with the before/after number, not just “improved.”

2. Communicate the outcome to the relevant staff and, where applicable, the Governing Body.

Technical source(s) for these steps:

National Accreditation Board for Hospitals and Healthcare Providers. (2025). NABH accreditation standards for hospitals (6th ed.), PSQ.4. ISBN 978-81-965264-9-8. https://portal.nabh.co/images/Standards/NABH%20Hospital%20Accreditation%20Standard%206th%20Edition%20January%202025.pdf

## 5.4 Capture patient-reported outcome measures

Why this step matters: A treatment can look successful on every clinical measure and still fail the patient in a way only they can report — that's exactly what PROMs catch and a clinical chart cannot.

1. Use a validated instrument — a generic one like EQ-5D (scoring mobility, self-care, usual activities, pain/discomfort, anxiety/depression, plus a visual analogue scale) for cross-condition comparison, or a disease-specific one (e.g. Oxford Knee Score) for sensitivity to one condition's outcomes.

2. Administer at defined time points — baseline and fixed post-treatment intervals — using a consistent mode (paper, tablet or app) to avoid measurement bias.

3. Score using the instrument's own official algorithm, and feed the result into the patient's care record and clinical discussion, not just an aggregate report.

4. Track change against the instrument's published Minimal Clinically Important Difference (MCID) to judge whether a change is actually meaningful to the patient.

Technical source(s) for these steps:

Office of Health Economics. (n.d.). EQ-5D and PROMs.

# 6. Stop-Work Authority

Any staff member covered by this SOP has the explicit right to pause or refuse to proceed with an unsafe step described below — this is not a disciplinary matter, even if it later turns out the step would have been fine.

Fewer than two quality improvement projects completed in a year is CORE non-compliance. The organisation must undertake at least two quality improvement projects per year. Failure to meet this minimum constitutes the specified stop-work trigger.

# 7. Records

This SOP produces and maintains Records 1 through 7 (see the PSQ.4 Records folder).

# 8. Related Documents

Policy on Quality Improvement Projects (HCO/PSQ/POL/04) — this policy

Required Records — PSQ.4 (see PSQ.4 Records folder)

# 9. Where This SOP's Requirements Come From (Verified Sources)

National Accreditation Board for Hospitals and Healthcare Providers. (2025). NABH accreditation standards for hospitals (6th ed.), PSQ.4. ISBN 978-81-965264-9-8. https://portal.nabh.co/images/Standards/NABH%20Hospital%20Accreditation%20Standard%206th%20Edition%20January%202025.pdf

# 10. Review

This SOP is reviewed at least annually by the Quality Coordinator together with the Safety/Quality Committee, using the outcomes of the annual programme review, and immediately if an audit or incident analysis finds it isn't working as written.